## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Physics engine does't work | 8 | 100 | 800 | 2023-03-24 | Accepted | A | Projectiles won't exist for very long so the small energy losses over time would not affect anything in a serious way. If something else crops up that exasterbates this issue then it can become another item
ITC doesn't work as expected | 8 | 40 | 320 | 2023-03-24 | Resolved | R | Now with nearly every task implemented I can see that everything is worked extremely well. My current bugs are do to edge cases not being implemented and not something systemic.
I don't have enough time to work on project and I fall behind | 8 | 70 | 560 | 2023-03-24 | Mitigated | M | More precise time-management will be employed and weekly checkins will keep me accountable
Time estimates are lower than the time spent | 70 | 13 | 910 | 2023-03-24 | Mitigated | M | I increase time estimate values and adjust schedule accordingly. RTOS > partying
Graphics take too long to create | 20 | 13 | 260 | 2023-03-24 | Resolved | R | Making the first few macros took very little time and the method I have for it is fast for prototyping and fine-tuning.
I require over 100% CPU util to accomplish goals | 2 | 70 | 140 | 2023-03-24 | Resolved | R | All the tasks that do computation are extremely quick, running on the order of 10s to 100s of micro seconds. The longest task that needs to run is the display task which runs for about 20ms, well below its 100ms period
Physics engine take too long to debug | 3 | 40 | 120 | 2023-03-24 | Resolved | R | The method I am using of divying up the physics task into different sub-systems is working well.
Data structures don't hold data / perform as expected | 8 | 20 | 160 | 2023-03-24 | Resolved | R | Data structures are consistently working and mutexing for data races has worked to keep data coherent.
Test Ball doesn't have constant energy | 100 | 1 | 100 | 2023-04-06 | Accepted | A | Projectiles won't exist for very long so the small energy losses over time would not affect anything in a serious way. If something else crops up that exasterbates this issue then it can become another item
Physics and display tasks timers aren't fast enough | 13 | 40 | 520 | 2023-04-06 | Resolved | R | These tasks are fast and using OSTimeDelay() with the desired period is working well for running tasks periodically.
Project specifics aren't in line with my implementations and would take to long to pivot | 5 | 13 | 65 | 2023-04-13

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100